## Cash Flow Summary
CASH FLOW SUMMARY BY MONTH
MONTH | AMOUNT | Major Milestones
Month 1 | 44560931.5 | Start
Month 2 | 13154756.2671 | Site Civil Starts
Month 3 | 12707317.2103 | Site Infrastructure
Month 4 | 11794117.0195
Month 5 | 11612292.2649
Month 6 | 11380531.3238
Month 7 | 5735865.7785
Month 8 | 6069824.1363
Month 9 | 8963134.0941
Month 10 | 10995583.9637
Month 11 | 19253896.4354
Month 12 | 19466706.573
Month 13 | 20019090.5405 | Verticle Construction Starts
Month 14 | 20023511.6729
Month 15 | 24733849.7807
Month 16 | 21337866.699
Month 17 | 21142346.1717
Month 18 | 21528096.7762
Month 19 | 83392238.0152
Month 20 | 45005266.9506
Month 21 | 45514951.3948
Month 22 | 44804844.4668
Month 23 | 47709640.9919
Month 24 | 47988431.077
Month 25 | 84104468.1007
Month 26 | 84595559.1198
Month 27 | 82676138.6991
Month 28 | 83158895.5053
Month 29 | 80753000.5555 | FF&E Purchase & Installation
Month 30 | 81224536.6983
Month 31 | 82287988.9325
Month 32 | 82768476.7529
Month 33 | 83251766.1851
Month 34 | 83737873.557
Month 35 | 115429178.5306
Month 36 | 119127984.9349
Month 37 | 80807744.6531
Month 38 | 99219590.1004
Month 39 | 86598836.6649
Month 40 | 84714460.8421
Month 41 | 51656728.2525
Month 42 | 106687000
TOTAL | 2191695319.1888
NOTE: The actual amount draw may vary slightly as the final design is completed.
Interest Calculation
Month 1 | 259938.7671 | 259938.7671
Month 2 | 338191.1548 | 337499.7103
Month 3 | 412317.1718 | 410966.1861
Month 4 | 481116.1878 | 479141.4316
Month 5 | 548854.5593 | 547380.4905
Month 6 | 615240.9921 | 614266.8514
Month 7 | 648700.2091 | 648225.2093
Month 8 | 684107.5166 | 684130.842
Month 9 | 736392.4654 | 736913.2723
Month 10 | 800533.3719 | 801550.7991
Month 11 | 912847.7678 | 914360.9367
Month 12 | 1026403.5561 | 1028411.5709
Month 13 | 1143181.5843 | 1145683.5316
Month 14 | 1259985.4024 | 1262980.3516
Month 15 | 1404266.1927 | 1407753.1959
Month 16 | 1528737.0818 | 1532715.1735
Month 17 | 1652067.4345 | 1656535.632
Month 18 | 1777647.999 | 1782605.3022
Month 19 | 2264102.7208 | 2269548.1124
Month 20 | 2526633.4447 | 2532565.8899
Month 21 | 2792137.3278 | 2798555.7747
Month 22 | 3053498.9205 | 3060402.2999
Month 23 | 3331805.1596 | 3339192.3849
Month 24 | 3611737.6742 | 3619607.6419
Month 25 | 4102347.0715 | 4110698.661
Month 26 | 4595821.1664 | 4604653.2404
Month 27 | 5078098.6421 | 5087410.0465
Month 28 | 5563192.1992 | 5572981.7634
Month 29 | 6034251.3691 | 6044517.9063
Month 30 | 6508061.1665 | 6518803.4737
Month 31 | 6988074.4353 | 6999291.2941
Month 32 | 7470890.5497 | 7482580.7263
Month 33 | 7956525.8525 | 7968688.0982
Month 34 | 8444996.7815 | 8457629.8336
Month 35 | 9118333.6563 | 9131436.2378
Month 36 | 9813246.9017 | 9826817.7226
Month 37 | 10284625.4122 | 10298663.1699
Month 38 | 10863406.3545 | 10877909.7345
Month 39 | 11368566.235 | 11383533.9117
Month 40 | 11862733.9233 | 11878164.5604
Month 41 | 12164064.8381 | 12179957.0901
Month 42 | 12786405.6714 | 12802297.9234
| 184814086.8885 | 185096966.7518

## Cash Flow Detail Myriad 2
SEPTEMBER 24, 2006
THESE BUDGETS ARE BEST ESTIMATES BASED ON CONCEPT PLANS TO DATE
& REFLECT CURRENT COSTS FOR SIMILAR PROJECTS
BUDGETS ARE SUBJECT TO FINAL PLANS & SPECIFICATIONS |  | CAPITAL
ESTIMATES
| DESCRIPTION | ITEM COST | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Total
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45
10 | LAND | 43680000 | 1: 11680000; 4: 32000000 | 43680000
0
| ACRES | 513 | [45 empty] | 0
|  |  | LAND & MOBILIZATION |  |  | LAND, SITE CIVIL, SITE INFRASTRUCTURE, DESIGN & SOFT COSTS
10 | GENERAL CONSTRUCTION |  | 4: PHASE 1 INFRASTRUCTURE & BUILDING PAD PREPARATION
50 | Site & Infrastructure | 21000000 | 14: 1166666.6667; 15: 1166666.6667; 16: 1166666.6667; 17: 1166666.6667; 18: 1166666.6667; 19: 1166666.6667; 20: 1166666.6667; 21: 1166666.6667; 22: 1166666.6667; 23: 1166666.6667; 24: 1166666.6667; 25: 1166666.6667; 26: 1166666.6667; 27: 1166666.6667; 28: 1166666.6667; 29: 1166666.6667; 30: 1166666.6667; 31: 1166666.6667 | 21000000 | 0
| Clear & Grub Phase 1 | 150000 | 4: 150000 | 150000 | 0
| Site Cut & Fill | 6125000 | 4: 1020833.3333; 5: 1020833.3333; 6: 1020833.3333; 7: 1020833.3333; 8: 1020833.3333; 9: 1020833.3333 | 6125000 | 0
| Offsite Borrow | 42000000 | 4: 7000000; 5: 7000000; 6: 7000000; 7: 7000000; 8: 7000000; 9: 7000000 | 42000000 | 0
| Cement Stabilized Base & Gravel | 1250000 | 6: 1250000 | 1250000 | 0
| Erosion Control | 1500000 | 5: 1500000 | 1500000 | 0
| Water lines Across Levee | 300000 | 7: 150000; 8: 150000 | 300000 | 0
| Box Culvert | 500000 | 5: 500000 | 500000 | 0
| Structures West of Levee | 500000 | 4: 83333.3333; 5: 83333.3333; 6: 83333.3333; 7: 83333.3333; 8: 83333.3333; 9: 83333.3333 | 500000 | 0
| General Conditions | 500000 | 4: 83333.3333; 5: 83333.3333; 6: 83333.3333; 7: 83333.3333; 8: 83333.3333; 9: 83333.3333 | 500000 | 0
| GC OH & P | 602500 | 4: 100416.6667; 5: 100416.6667; 6: 100416.6667; 7: 100416.6667; 8: 100416.6667; 9: 100416.6667 | 602500 | 0
| Permit | 31631 | 4: 31631 | 31631 | 0
| Builder's Risk Ins | 69589 | 4: 69589 | 69589 | 0
| Bond | 94894 | 4: 94894 | 94894 | 0
| Gross Reciept Tax | 466405 | 4: 77734.1667; 5: 77734.1667; 6: 77734.1667; 7: 77734.1667; 8: 77734.1667; 9: 77734.1667 | 466405 | 0
| Engineering Fee Phase 1 | 1200000 | 4: 200000; 5: 200000; 6: 200000; 7: 200000; 8: 200000; 9: 200000 | 1200000 | 0
| Geotechinical | 150000 | 4: 75000; 6: 75000 | 150000 | 0
| Topo Survey | 75000 | 4: 50000; 6: 25000 | 75000 | 0
| Impact Fees | 200000 | 4: 200000 | 200000 | 0
| Contingency | 500000 | 4: 83333.3333; 5: 83333.3333; 6: 83333.3333; 7: 83333.3333; 8: 83333.3333; 9: 83333.3333 | 500000 | 0
55 | Public Entry Roads (Site work, paving , Levy crossing, steet lights) | 31046400 | 14: 1724800; 15: 1724800; 16: 1724800; 17: 1724800; 18: 1724800; 19: 1724800; 20: 1724800; 21: 1724800; 22: 1724800; 23: 1724800; 24: 1724800; 25: 1724800; 26: 1724800; 27: 1724800; 28: 1724800; 29: 1724800; 30: 1724800; 31: 1724800 | 31046400 | 0
60 | Site Civil | 19694535.5556 | 13: 3282422.5926; 14: 3282422.5926; 15: 3282422.5926; 16: 3282422.5926; 17: 3282422.5926; 18: 3282422.5926 | 19694535.5556 | 0
100 | Non-Golf Dome Structure | 26869830 | 22: 671745.75; 23: 671745.75; 24: 671745.75; 25: 671745.75; 26: 671745.75; 27: 671745.75; 28: 1567406.75; 29: 1567406.75; 30: 1567406.75; 31: 1567406.75; 32: 1567406.75; 33: 1567406.75; 34: 1567406.75; 35: 1567406.75; 36: 1567406.75; 37: 1567406.75; 38: 1567406.75; 39: 1567406.75; 40: 671745.75; 41: 671745.75; 42: 671745.75; 43: 671745.75; 44: 671745.75; 45: 671745.75 | 26869830 | 0
200 | Convention, meeting,office,etc.(=400,000) | 130000000 | 22: 3250000; 23: 3250000; 24: 3250000; 25: 3250000; 26: 3250000; 27: 3250000; 28: 7583333.3333; 29: 7583333.3333; 30: 7583333.3333; 31: 7583333.3333; 32: 7583333.3333; 33: 7583333.3333; 34: 7583333.3333; 35: 7583333.3333; 36: 7583333.3333; 37: 7583333.3333; 38: 7583333.3333; 39: 7583333.3333; 40: 3250000; 41: 3250000; 42: 3250000; 43: 3250000; 44: 3250000; 45: 3250000 | 130000000 | 0
200 | Convention Space add 200,000 after Ramp up
300 | 1200 Keys @800 FAR HOTEL | 182400000 | 22: 4560000; 23: 4560000; 24: 4560000; 25: 4560000; 26: 4560000; 27: 4560000; 28: 10640000; 29: 10640000; 30: 10640000; 31: 10640000; 32: 10640000; 33: 10640000; 34: 10640000; 35: 10640000; 36: 10640000; 37: 10640000; 38: 10640000; 39: 10640000; 40: 4560000; 41: 4560000; 42: 4560000; 43: 4560000; 44: 4560000; 45: 4560000 | 182400000 | 0
301 | 500 Key Casino # 1 HOTEL | 70000000 | 22: 1750000; 23: 1750000; 24: 1750000; 25: 1750000; 26: 1750000; 27: 1750000; 28: 4083333.3333; 29: 4083333.3333; 30: 4083333.3333; 31: 4083333.3333; 32: 4083333.3333; 33: 4083333.3333; 34: 4083333.3333; 35: 4083333.3333; 36: 4083333.3333; 37: 4083333.3333; 38: 4083333.3333; 39: 4083333.3333; 40: 1750000; 41: 1750000; 42: 1750000; 43: 1750000; 44: 1750000; 45: 1750000 | 70000000 | 0
301 | 500 Key Casino # 2 HOTEL | 70000000 | 22: 1750000; 23: 1750000; 24: 1750000; 25: 1750000; 26: 1750000; 27: 1750000; 28: 4083333.3333; 29: 4083333.3333; 30: 4083333.3333; 31: 4083333.3333; 32: 4083333.3333; 33: 4083333.3333; 34: 4083333.3333; 35: 4083333.3333; 36: 4083333.3333; 37: 4083333.3333; 38: 4083333.3333; 39: 4083333.3333; 40: 1750000; 41: 1750000; 42: 1750000; 43: 1750000; 44: 1750000; 45: 1750000 | 70000000 | 0
325 | Residential Units 50ea | 15625000 | 22: 390625; 23: 390625; 24: 390625; 25: 390625; 26: 390625; 27: 390625; 28: 911458.3333; 29: 911458.3333; 30: 911458.3333; 31: 911458.3333; 32: 911458.3333; 33: 911458.3333; 34: 911458.3333; 35: 911458.3333; 36: 911458.3333; 37: 911458.3333; 38: 911458.3333; 39: 911458.3333; 40: 390625; 41: 390625; 42: 390625; 43: 390625; 44: 390625; 45: 390625 | 15625000 | 0
350 | Health Club & Spa 40,000 SF | 12500000 | 22: 312500; 23: 312500; 24: 312500; 25: 312500; 26: 312500; 27: 312500; 28: 729166.6667; 29: 729166.6667; 30: 729166.6667; 31: 729166.6667; 32: 729166.6667; 33: 729166.6667; 34: 729166.6667; 35: 729166.6667; 36: 729166.6667; 37: 729166.6667; 38: 729166.6667; 39: 729166.6667; 40: 312500; 41: 312500; 42: 312500; 43: 312500; 44: 312500; 45: 312500 | 12500000 | 0
400 | Casino (1 @ 160000sf ea) | 56000000 | 22: 1400000; 23: 1400000; 24: 1400000; 25: 1400000; 26: 1400000; 27: 1400000; 28: 3266666.6667; 29: 3266666.6667; 30: 3266666.6667; 31: 3266666.6667; 32: 3266666.6667; 33: 3266666.6667; 34: 3266666.6667; 35: 3266666.6667; 36: 3266666.6667; 37: 3266666.6667; 38: 3266666.6667; 39: 3266666.6667; 40: 1400000; 41: 1400000; 42: 1400000; 43: 1400000; 44: 1400000; 45: 1400000 | 56000000 | 0
400 | Casino (2 @ 160000sf ea) | 56000000 | 22: 1400000; 23: 1400000; 24: 1400000; 25: 1400000; 26: 1400000; 27: 1400000; 28: 3266666.6667; 29: 3266666.6667; 30: 3266666.6667; 31: 3266666.6667; 32: 3266666.6667; 33: 3266666.6667; 34: 3266666.6667; 35: 3266666.6667; 36: 3266666.6667; 37: 3266666.6667; 38: 3266666.6667; 39: 3266666.6667; 40: 1400000; 41: 1400000; 42: 1400000; 43: 1400000; 44: 1400000; 45: 1400000 | 56000000
550 | Parking Deck 7000 SPACES | 73500000 | 22: 1837500; 23: 1837500; 24: 1837500; 25: 1837500; 26: 1837500; 27: 1837500; 28: 4287500; 29: 4287500; 30: 4287500; 31: 4287500; 32: 4287500; 33: 4287500; 34: 4287500; 35: 4287500; 36: 4287500; 37: 4287500; 38: 4287500; 39: 4287500; 40: 1837500; 41: 1837500; 42: 1837500; 43: 1837500; 44: 1837500; 45: 1837500 | 73500000 | 0
600 | Interior Landscaping | 17968500 | 22: 449212.5; 23: 449212.5; 24: 449212.5; 25: 449212.5; 26: 449212.5; 27: 449212.5; 28: 1048162.5; 29: 1048162.5; 30: 1048162.5; 31: 1048162.5; 32: 1048162.5; 33: 1048162.5; 34: 1048162.5; 35: 1048162.5; 36: 1048162.5; 37: 1048162.5; 38: 1048162.5; 39: 1048162.5; 40: 449212.5; 41: 449212.5; 42: 449212.5; 43: 449212.5; 44: 449212.5; 45: 449212.5 | 17968500 | 0
650 | Exterior Landscaping | 6534000 | 22: 163350; 23: 163350; 24: 163350; 25: 163350; 26: 163350; 27: 163350; 28: 381150; 29: 381150; 30: 381150; 31: 381150; 32: 381150; 33: 381150; 34: 381150; 35: 381150; 36: 381150; 37: 381150; 38: 381150; 39: 381150; 40: 163350; 41: 163350; 42: 163350; 43: 163350; 44: 163350; 45: 163350 | 6534000 | 0
650 | Hardscape | 40500000 | 22: 1012500; 23: 1012500; 24: 1012500; 25: 1012500; 26: 1012500; 27: 1012500; 28: 2362500; 29: 2362500; 30: 2362500; 31: 2362500; 32: 2362500; 33: 2362500; 34: 2362500; 35: 2362500; 36: 2362500; 37: 2362500; 38: 2362500; 39: 2362500; 40: 1012500; 41: 1012500; 42: 1012500; 43: 1012500; 44: 1012500; 45: 1012500 | 40500000 | 0
800 | Solar Roof Dome | 50000000 | 22: 1250000; 23: 1250000; 24: 1250000; 25: 1250000; 26: 1250000; 27: 1250000; 28: 2916666.6667; 29: 2916666.6667; 30: 2916666.6667; 31: 2916666.6667; 32: 2916666.6667; 33: 2916666.6667; 34: 2916666.6667; 35: 2916666.6667; 36: 2916666.6667; 37: 2916666.6667; 38: 2916666.6667; 39: 2916666.6667; 40: 1250000; 41: 1250000; 42: 1250000; 43: 1250000; 44: 1250000; 45: 1250000 | 50000000 | 0
810 | Golf Academy | 937500 | 22: 23437.5; 23: 23437.5; 24: 23437.5; 25: 23437.5; 26: 23437.5; 27: 23437.5; 28: 54687.5; 29: 54687.5; 30: 54687.5; 31: 54687.5; 32: 54687.5; 33: 54687.5; 34: 54687.5; 35: 54687.5; 36: 54687.5; 37: 54687.5; 38: 54687.5; 39: 54687.5; 40: 23437.5; 41: 23437.5; 42: 23437.5; 43: 23437.5; 44: 23437.5; 45: 23437.5 | 937500 | 0
815 | Golf Clubhouse and Golf Course | 18000000 | 22: 450000; 23: 450000; 24: 450000; 25: 450000; 26: 450000; 27: 450000; 28: 1050000; 29: 1050000; 30: 1050000; 31: 1050000; 32: 1050000; 33: 1050000; 34: 1050000; 35: 1050000; 36: 1050000; 37: 1050000; 38: 1050000; 39: 1050000; 40: 450000; 41: 450000; 42: 450000; 43: 450000; 44: 450000; 45: 450000 | 18000000 | 0
815 | Top Golf | 5000000 | 22: 125000; 23: 125000; 24: 125000; 25: 125000; 26: 125000; 27: 125000; 28: 291666.6667; 29: 291666.6667; 30: 291666.6667; 31: 291666.6667; 32: 291666.6667; 33: 291666.6667; 34: 291666.6667; 35: 291666.6667; 36: 291666.6667; 37: 291666.6667; 38: 291666.6667; 39: 291666.6667; 40: 125000; 41: 125000; 42: 125000; 43: 125000; 44: 125000; 45: 125000 | 5000000 | 0
815 | Golf Course site work | 8000000 | 22: 200000; 23: 200000; 24: 200000; 25: 200000; 26: 200000; 27: 200000; 28: 466666.6667; 29: 466666.6667; 30: 466666.6667; 31: 466666.6667; 32: 466666.6667; 33: 466666.6667; 34: 466666.6667; 35: 466666.6667; 36: 466666.6667; 37: 466666.6667; 38: 466666.6667; 39: 466666.6667; 40: 200000; 41: 200000; 42: 200000; 43: 200000; 44: 200000; 45: 200000 | 8000000 | 0
820 | Tennis Academy | 937500 | 22: 23437.5; 23: 23437.5; 24: 23437.5; 25: 23437.5; 26: 23437.5; 27: 23437.5; 28: 54687.5; 29: 54687.5; 30: 54687.5; 31: 54687.5; 32: 54687.5; 33: 54687.5; 34: 54687.5; 35: 54687.5; 36: 54687.5; 37: 54687.5; 38: 54687.5; 39: 54687.5; 40: 23437.5; 41: 23437.5; 42: 23437.5; 43: 23437.5; 44: 23437.5; 45: 23437.5 | 937500 | 0
840 | Dog Kennels | 500000 | 22: 12500; 23: 12500; 24: 12500; 25: 12500; 26: 12500; 27: 12500; 28: 29166.6667; 29: 29166.6667; 30: 29166.6667; 31: 29166.6667; 32: 29166.6667; 33: 29166.6667; 34: 29166.6667; 35: 29166.6667; 36: 29166.6667; 37: 29166.6667; 38: 29166.6667; 39: 29166.6667; 40: 12500; 41: 12500; 42: 12500; 43: 12500; 44: 12500; 45: 12500 | 500000 | 0
850 | Additional Domes & Structures | 35000000 | 22: 875000; 23: 875000; 24: 875000; 25: 875000; 26: 875000; 27: 875000; 28: 2041666.6667; 29: 2041666.6667; 30: 2041666.6667; 31: 2041666.6667; 32: 2041666.6667; 33: 2041666.6667; 34: 2041666.6667; 35: 2041666.6667; 36: 2041666.6667; 37: 2041666.6667; 38: 2041666.6667; 39: 2041666.6667; 40: 875000; 41: 875000; 42: 875000; 43: 875000; 44: 875000; 45: 875000 | 35000000 | 0
860 | Plant Stagging | 6732650 | 22: 168316.25; 23: 168316.25; 24: 168316.25; 25: 168316.25; 26: 168316.25; 27: 168316.25; 28: 392737.9167; 29: 392737.9167; 30: 392737.9167; 31: 392737.9167; 32: 392737.9167; 33: 392737.9167; 34: 392737.9167; 35: 392737.9167; 36: 392737.9167; 37: 392737.9167; 38: 392737.9167; 39: 392737.9167; 40: 168316.25; 41: 168316.25; 42: 168316.25; 43: 168316.25; 44: 168316.25; 45: 168316.25 | 6732650 | 0
900 | Retail (250,000 SF) | 22500000 | 22: 562500; 23: 562500; 24: 562500; 25: 562500; 26: 562500; 27: 562500; 28: 1312500; 29: 1312500; 30: 1312500; 31: 1312500; 32: 1312500; 33: 1312500; 34: 1312500; 35: 1312500; 36: 1312500; 37: 1312500; 38: 1312500; 39: 1312500; 40: 562500; 41: 562500; 42: 562500; 43: 562500; 44: 562500; 45: 562500 | 22500000 | 0
| sub-total "Category 10" | 1033460934.5556 | [45 empty] | 1033460934.5556 | 0
0
15 | VENUES | [47 empty] | 0
700 | Family Entertainment Center | 13714500 | 22: 342862.5; 23: 342862.5; 24: 342862.5; 25: 342862.5; 26: 342862.5; 27: 342862.5; 28: 800012.5; 29: 800012.5; 30: 800012.5; 31: 800012.5; 32: 800012.5; 33: 800012.5; 34: 800012.5; 35: 800012.5; 36: 800012.5; 37: 800012.5; 38: 800012.5; 39: 800012.5; 40: 342862.5; 41: 342862.5; 42: 342862.5; 43: 342862.5; 44: 342862.5; 45: 342862.5 | 13714500 | 0
700 | Theater 2500 seats | 20000000 | 22: 500000; 23: 500000; 24: 500000; 25: 500000; 26: 500000; 27: 500000; 28: 1166666.6667; 29: 1166666.6667; 30: 1166666.6667; 31: 1166666.6667; 32: 1166666.6667; 33: 1166666.6667; 34: 1166666.6667; 35: 1166666.6667; 36: 1166666.6667; 37: 1166666.6667; 38: 1166666.6667; 39: 1166666.6667; 40: 500000; 41: 500000; 42: 500000; 43: 500000; 44: 500000; 45: 500000 | 20000000 | 0
700 | Mississippi Eye | 34403613 | 12: 860090.325; 23: 860090.325; 24: 860090.325; 25: 860090.325; 26: 860090.325; 27: 860090.325; 28: 2006877.425; 29: 2006877.425; 30: 2006877.425; 31: 2006877.425; 32: 2006877.425; 33: 2006877.425; 34: 2006877.425; 35: 2006877.425; 36: 2006877.425; 37: 2006877.425; 38: 2006877.425; 39: 2006877.425; 40: 860090.325; 41: 860090.325; 42: 860090.325; 43: 860090.325; 44: 860090.325; 45: 860090.325 | 34403613 | 0
700 | Millimium Water Projection Theater | 5000000 | 22: 125000; 23: 125000; 24: 125000; 25: 125000; 26: 125000; 27: 125000; 28: 291666.6667; 29: 291666.6667; 30: 291666.6667; 31: 291666.6667; 32: 291666.6667; 33: 291666.6667; 34: 291666.6667; 35: 291666.6667; 36: 291666.6667; 37: 291666.6667; 38: 291666.6667; 39: 291666.6667; 40: 125000; 41: 125000; 42: 125000; 43: 125000; 44: 125000; 45: 125000 | 5000000 | 0
700 | Lucid Digital Multi-Media Night Club | 6300000 | 12: 157500; 23: 157500; 24: 157500; 25: 157500; 26: 157500; 27: 157500; 28: 367500; 29: 367500; 30: 367500; 31: 367500; 32: 367500; 33: 367500; 34: 367500; 35: 367500; 36: 367500; 37: 367500; 38: 367500; 39: 367500; 40: 157500; 41: 157500; 42: 157500; 43: 157500; 44: 157500; 45: 157500 | 6300000 | 0
| Select Design Group | 600000 | 4: 100000; 5: 100000; 6: 100000; 7: 100000; 8: 100000; 9: 100000; 10: 100000 | 600000 | 0
700 | Caves of Music | 6000000 | 12: 150000; 23: 150000; 24: 150000; 25: 150000; 26: 150000; 27: 150000; 28: 350000; 29: 350000; 30: 350000; 31: 350000; 32: 350000; 33: 350000; 34: 350000; 35: 350000; 36: 350000; 37: 350000; 38: 350000; 39: 350000; 40: 150000; 41: 150000; 42: 150000; 43: 150000; 44: 150000; 45: 150000 | 6000000 | 0
700 | Ice Cavern | 12000000 | 12: 300000; 23: 300000; 24: 300000; 25: 300000; 26: 300000; 27: 300000; 28: 700000; 29: 700000; 30: 700000; 31: 700000; 32: 700000; 33: 700000; 34: 700000; 35: 700000; 36: 700000; 37: 700000; 38: 700000; 39: 700000; 40: 300000; 41: 300000; 42: 300000; 43: 300000; 44: 300000; 45: 300000 | 12000000 | 0
700 | Snow Park | 15692560 | 12: 392314; 23: 392314; 24: 392314; 25: 392314; 26: 392314; 27: 392314; 28: 915399.3333; 29: 915399.3333; 30: 915399.3333; 31: 915399.3333; 32: 915399.3333; 33: 915399.3333; 34: 915399.3333; 35: 915399.3333; 36: 915399.3333; 37: 915399.3333; 38: 915399.3333; 39: 915399.3333; 40: 392314; 41: 392314; 42: 392314; 43: 392314; 44: 392314; 45: 392314 | 15692560 | 0
700 | Aquarina | 11700000 | 12: 292500; 23: 292500; 24: 292500; 25: 292500; 26: 292500; 27: 292500; 28: 682500; 29: 682500; 30: 682500; 31: 682500; 32: 682500; 33: 682500; 34: 682500; 35: 682500; 36: 682500; 37: 682500; 38: 682500; 39: 682500; 40: 292500; 41: 292500; 42: 292500; 43: 292500; 44: 292500; 45: 292500 | 11700000 | 0
700 | Water Park ( Interior ) | 20000000 | 22: 500000; 23: 500000; 24: 500000; 25: 500000; 26: 500000; 27: 500000; 28: 1166666.6667; 29: 1166666.6667; 30: 1166666.6667; 31: 1166666.6667; 32: 1166666.6667; 33: 1166666.6667; 34: 1166666.6667; 35: 1166666.6667; 36: 1166666.6667; 37: 1166666.6667; 38: 1166666.6667; 39: 1166666.6667; 40: 500000; 41: 500000; 42: 500000; 43: 500000; 44: 500000; 45: 500000 | 20000000 | 0
| sub-total "Category 15" | 145410673 | [45 empty] | 145410673 | 0
0
20 | INFRASTRUCTURE | [47 empty] | 0
100 | Infrastructure | 29403000 | 22: 735075; 23: 735075; 24: 735075; 25: 735075; 26: 735075; 27: 735075; 28: 1715175; 29: 1715175; 30: 1715175; 31: 1715175; 32: 1715175; 33: 1715175; 34: 1715175; 35: 1715175; 36: 1715175; 37: 1715175; 38: 1715175; 39: 1715175; 40: 735075; 41: 735075; 42: 735075; 43: 735075; 44: 735075; 45: 735075 | 29403000 | 0
| sub-total "Category 20" | 29403000 | [45 empty] | 29403000 | 0
0
30 | DESIGN CONSULTANTS | [47 empty] | 0
100 | Architects | 36382621.52 | [9 empty] | 454782.769 | 454782.769 | 454782.769 | 454782.769 | 1819131.076 | 1819131.076 | 1819131.076 | 1819131.076 | 5002610.459 | 5002610.459 | 5002610.459 | 5002610.459 | 303188.5127 | 303188.5127 | 303188.5127 | 303188.5127 | 303188.5127 | 303188.5127 | 303188.5127 | 303188.5127 | 303188.5127 | 303188.5127 | 303188.5127 | 303188.5127 | 303188.5127 | 303188.5127 | 303188.5127 | 303188.5127 | 303188.5127 | 303188.5127 | 303188.5127 | 303188.5127 | 303188.5127 | 303188.5127 | 303188.5127 | 303188.5127 | 36382621.52 | 0
100 PH 1 | Milton Pate & Assoc | 1500000 | 4: 250000; 5: 250000; 6: 250000; 7: 250000; 8: 250000; 9: 250000 | 1500000 | 0
| Heilein, Schrock, Sterns Arena Design | 150000 | 7: 75000; 8: 75000 | 150000 | 0
105 | Concept & Design Mgt | 5000000 | 11: 500000; 12: 500000; 13: 500000; 14: 500000; 15: 500000; 16: 500000; 17: 333333.3333; 18: 333333.3333; 19: 333333.3333; 20: 333333.3333; 21: 333333.3333; 22: 333333.3333 | 5000000 | 0
105 PH 1 | Paul Ma Design | 750000 | 4: 125000; 5: 125000; 6: 125000; 7: 125000; 8: 125000; 9: 125000 | 750000 | 0
105 | Casino Design | 3000000 | [9 empty] | 75000 | 75000 | 75000 | 75000 | 112500 | 112500 | 112500 | 112500 | 412500 | 412500 | 412500 | 412500 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 3000000 | 0
| PH 1 Casino Design | 350000 | 6: 175000; 7: 175000 | 350000 | 0
110 | Structural Engineer | 8064000 | [17 empty] | 201600 | 201600 | 201600 | 201600 | 302400 | 302400 | 302400 | 302400 | 1108800 | 1108800 | 1108800 | 1108800 | 100800 | 100800 | 100800 | 100800 | 100800 | 100800 | 100800 | 100800 | 100800 | 100800 | 100800 | 100800 | 100800 | 100800 | 100800 | 100800 | 8064000 | 0
120 | MEP Engineer | 15128000 | [17 empty] | 378200 | 378200 | 378200 | 378200 | 567300 | 567300 | 567300 | 567300 | 2080100 | 2080100 | 2080100 | 2080100 | 189100 | 189100 | 189100 | 189100 | 189100 | 189100 | 189100 | 189100 | 189100 | 189100 | 189100 | 189100 | 189100 | 189100 | 189100 | 189100 | 15128000 | 0
120 PH 1 | Allen & Hoshall EOR | 1500000 | 4: 250000; 5: 250000; 6: 250000; 7: 250000; 8: 250000; 9: 250000 | 1500000 | 0
130 | Civil Engineer | 3800000 | 12: 380000; 13: 380000; 14: 380000; 15: 380000; 16: 380000; 17: 380000; 18: 253333.3333; 19: 253333.3333; 20: 253333.3333; 21: 253333.3333; 22: 253333.3333; 23: 253333.3333 | 3800000 | 0
150 | Code/Life Safety | 550000 | 22: 68750; 23: 68750; 24: 68750; 25: 68750; 26: 68750; 27: 68750; 28: 22916.6667; 29: 22916.6667; 30: 22916.6667; 31: 22916.6667; 32: 22916.6667; 33: 22916.6667 | 550000 | 0
160 | Acoustical | 100000 | 22: 16666.6667; 23: 16666.6667; 24: 16666.6667; 25: 16666.6667; 26: 16666.6667; 27: 16666.6667 | 100000 | 0
200 | Roofing & W.P. | 50000 | 22: 8333.3333; 23: 8333.3333; 24: 8333.3333; 25: 8333.3333; 26: 8333.3333; 27: 8333.3333 | 50000 | 0
210 | Landscape Ext. EDSA PH 1 | 150000 | 4: 75000; 5: 75000 | 150000 | 0
210 | Landscape Ext. EDSA | 1500000 | 22: 37500; 23: 37500; 24: 37500; 25: 37500; 26: 112500; 27: 112500; 28: 112500; 29: 112500; 30: 225000; 31: 225000; 32: 225000; 33: 225000 | 1500000 | 0
210 | NBS Water Park | 150000 | 6: 75000; 7: 75000 | 150000 | 0
300 | Elevator | 75000 | 22: 12500; 23: 12500; 24: 12500; 25: 12500; 26: 12500; 27: 12500 | 75000 | 0
400 | Food & Beverage | 180000 | 22: 30000; 23: 30000; 24: 30000; 25: 30000; 26: 30000; 27: 30000 | 180000 | 0
410 | Laundry | 75000 | 22: 12500; 23: 12500; 24: 12500; 25: 12500; 26: 12500; 27: 12500 | 75000 | 0
500 | Interior Design | 2000000 | 22: 50000; 23: 50000; 24: 50000; 25: 50000; 26: 150000; 27: 150000; 28: 150000; 29: 150000; 30: 300000; 31: 300000; 32: 300000; 33: 300000 | 2000000 | 0
510 | Lighting Designer | 200000 | 22: 5000; 23: 5000; 24: 5000; 25: 5000; 26: 15000; 27: 15000; 28: 15000; 29: 15000; 30: 30000; 31: 30000; 32: 30000; 33: 30000 | 200000 | 0
| Musco Lighting | 150000 | 7: 75000; 8: 75000 | 150000 | 0
520 | Landscape Int. | 1500000 | 22: 37500; 23: 37500; 24: 37500; 25: 37500; 26: 112500; 27: 112500; 28: 112500; 29: 112500; 30: 225000; 31: 225000; 32: 225000; 33: 225000 | 1500000 | 0
530 | Graphics | 1000000 | 22: 25000; 23: 25000; 24: 25000; 25: 25000; 26: 75000; 27: 75000; 28: 75000; 29: 75000; 30: 150000; 31: 150000; 32: 150000; 33: 150000 | 1000000 | 0
540 | Artwork | 100000 | 22: 2500; 23: 2500; 24: 2500; 25: 2500; 26: 7500; 27: 7500; 28: 7500; 29: 7500; 30: 15000; 31: 15000; 32: 15000; 33: 15000 | 100000 | 0
700 | Audio Visual/Security | 100000 | 22: 2500; 23: 2500; 24: 2500; 25: 2500; 26: 7500; 27: 7500; 28: 7500; 29: 7500; 30: 15000; 31: 15000; 32: 15000; 33: 15000 | 100000 | 0
720 | Telephone | 75000 | 22: 1875; 23: 1875; 24: 1875; 25: 1875; 26: 5625; 27: 5625; 28: 5625; 29: 5625; 30: 11250; 31: 11250; 32: 11250; 33: 11250 | 75000 | 0
800 | Exterior Wall | 75000 | 22: 12500; 23: 12500; 24: 12500; 25: 12500; 26: 12500; 27: 12500 | 75000 | 0
810 | Wind Engineering | 100000 | 22: 16666.6667; 23: 16666.6667; 24: 16666.6667; 25: 16666.6667; 26: 16666.6667; 27: 16666.6667 | 100000 | 0
820 | Dome Engineering | 3500000 | 10: 100000; 14: 288888.8889; 15: 388888.8889; 16: 388888.8889; 17: 388888.8889; 18: 388888.8889; 19: 388888.8889; 20: 388888.8889; 21: 388888.8889; 22: 388888.8889 | 3500000 | 0
850 | Golf Course Design | 1200000 | 13: 200000; 14: 200000; 15: 200000; 16: 200000; 17: 200000; 18: 200000 | 1200000 | 0
850 | Golf Course Dr Rogers, Bamboo, Etc | 350000 | 4: 58333.3333; 5: 58333.3333; 6: 58333.3333; 7: 58333.3333; 8: 58333.3333; 9: 58333.3333 | 350000 | 0
875 | Horticural Consultant | 150000 | 4: 25000; 5: 25000; 6: 25000; 7: 25000; 8: 25000; 9: 25000 | 150000 | 0
880 | Solargenix | 350000 | 4: 58333.3333; 5: 58333.3333; 6: 58333.3333; 7: 58333.3333; 8: 58333.3333; 9: 58333.3333 | 350000 | 0
900 | Geotechnical | 500000 | 10: 12500; 11: 12500; 12: 12500; 13: 12500; 14: 37500; 15: 37500; 16: 37500; 17: 37500; 18: 75000; 19: 75000; 20: 75000; 21: 75000 | 500000 | 0
900 | Topo & Borings PH 1 | 200000 | 4: 33333.3333; 5: 33333.3333; 6: 33333.3333; 7: 33333.3333; 8: 33333.3333; 9: 33333.3333 | 200000 | 0
910 | Reimbursables | 13470693.228 | [9 empty] | 112255.7769 | 112255.7769 | 112255.7769 | 112255.7769 | 374185.923 | 374185.923 | 374185.923 | 374185.923 | 374185.923 | 374185.923 | 374185.923 | 636116.0691 | 636116.0691 | 636116.0691 | 636116.0691 | 374185.923 | 374185.923 | 374185.923 | 374185.923 | 374185.923 | 374185.923 | 374185.923 | 374185.923 | 374185.923 | 374185.923 | 374185.923 | 374185.923 | 374185.923 | 374185.923 | 374185.923 | 374185.923 | 374185.923 | 374185.923 | 374185.923 | 374185.923 | 374185.923 | 13470693.228 | 0
| sub-total "Category 30" | 103475314.748 | [45 empty] | 103475314.748 | 0
0
40 | CONSTRUCTION CONSULTANTS | [47 empty] | 0
100 | Permits/Fees | 1216934.6076 | 22: 1216934.6076 | 1216934.6076 | 0
150 | Govermental Site Permits AYE | 500000 | 4: 166666.6667; 5: 166666.6667; 6: 166666.6667 | 500000 | 0
200 | Geotechnical Consulting | 300000 | 10: 50000; 11: 50000; 12: 50000; 13: 50000; 14: 50000; 15: 50000 | 300000 | 0
300 | Surveyor | 450000 | 10: 75000; 11: 75000; 12: 75000; 13: 75000; 14: 75000; 15: 75000 | 450000 | 0
310 | Preconstruction Survey | 50000 | 12: 50000 | 50000 | 0
400 | Parking | 350000 | 13: 58333.3333; 14: 58333.3333; 15: 58333.3333; 16: 58333.3333; 17: 58333.3333; 18: 58333.3333 | 350000 | 0
410 | Traffic | 350000 | 13: 70000; 14: 70000; 15: 70000; 16: 70000; 17: 70000 | 350000 | 0
500 | Testing/Quality Assurance | 650000 | 22: 27083.3333; 23: 27083.3333; 24: 27083.3333; 25: 27083.3333; 26: 27083.3333; 27: 27083.3333; 28: 27083.3333; 29: 27083.3333; 30: 27083.3333; 31: 27083.3333; 32: 27083.3333; 33: 27083.3333; 34: 27083.3333; 35: 27083.3333; 36: 27083.3333; 37: 27083.3333; 38: 27083.3333; 39: 27083.3333; 40: 27083.3333; 41: 27083.3333; 42: 27083.3333; 43: 27083.3333; 44: 27083.3333; 45: 27083.3333 | 650000 | 0
510 | Threshold Inspection | 350000 | 22: 14583.3333; 23: 14583.3333; 24: 14583.3333; 25: 14583.3333; 26: 14583.3333; 27: 14583.3333; 28: 14583.3333; 29: 14583.3333; 30: 14583.3333; 31: 14583.3333; 32: 14583.3333; 33: 14583.3333; 34: 14583.3333; 35: 14583.3333; 36: 14583.3333; 37: 14583.3333; 38: 14583.3333; 39: 14583.3333; 40: 14583.3333; 41: 14583.3333; 42: 14583.3333; 43: 14583.3333; 44: 14583.3333; 45: 14583.3333 | 350000 | 0
600 | Utility Connection & Impact Fees | 8000000 | 22: 8000000 | 8000000 | 0
700 | Environmental | 275000 | 12: 275000 | 275000 | 0
800 | Scheduling | 300000 | 10: 25000; 11: 25000; 12: 25000; 13: 25000; 14: 25000; 15: 25000; 16: 25000; 17: 25000; 18: 25000; 19: 25000; 20: 25000; 21: 25000 | 300000 | 0
810 | Cost Estimating | 400000 | 10: 33333.3333; 11: 33333.3333; 12: 33333.3333; 13: 33333.3333; 14: 33333.3333; 15: 33333.3333; 16: 33333.3333; 17: 33333.3333; 18: 33333.3333; 19: 33333.3333; 20: 33333.3333; 21: 33333.3333 | 400000 | 0
900 | Other | 100000 | 10: 8333.3333; 11: 8333.3333; 12: 8333.3333; 13: 8333.3333; 14: 8333.3333; 15: 8333.3333; 16: 8333.3333; 17: 8333.3333; 18: 8333.3333; 19: 8333.3333; 20: 8333.3333; 21: 8333.3333 | 100000 | 0
| sub-total "Category 40" | 13291934.6076 | [45 empty] | 13291934.6076 | 0
0
50 | BUILDING CONTIGENCY | [47 empty] | 0
100 | Building Contingency | 35366148.2267 | 22: 1473589.5094; 23: 1473589.5094; 24: 1473589.5094; 25: 1473589.5094; 26: 1473589.5094; 27: 1473589.5094; 28: 1473589.5094; 29: 1473589.5094; 30: 1473589.5094; 31: 1473589.5094; 32: 1473589.5094; 33: 1473589.5094; 34: 1473589.5094; 35: 1473589.5094; 36: 1473589.5094; 37: 1473589.5094; 38: 1473589.5094; 39: 1473589.5094; 40: 1473589.5094; 41: 1473589.5094; 42: 1473589.5094; 43: 1473589.5094; 44: 1473589.5094; 45: 1473589.5094 | 35366148.2267 | 0
| sub-total "Category 50" | 35366148.2267 | [45 empty] | 35366148.2267 | 0
0
0
20 | BUILDING TOTAL CAT.(10+15+20+30+40+50) | 1404088005.1378 | [45 empty] | 1404088005.1378 | 0
0
0
| Feasibility Study/Site Valuation | 185000 | 13: 61666.6667; 14: 61666.6667; 15: 61666.6667 | 185000 | 0
| Legal Fees | 250000 | [9 empty] | 6944.4444 | 6944.4444 | 6944.4444 | 6944.4444 | 6944.4444 | 6944.4444 | 6944.4444 | 6944.4444 | 6944.4444 | 6944.4444 | 6944.4444 | 6944.4444 | 6944.4444 | 6944.4444 | 6944.4444 | 6944.4444 | 6944.4444 | 6944.4444 | 6944.4444 | 6944.4444 | 6944.4444 | 6944.4444 | 6944.4444 | 6944.4444 | 6944.4444 | 6944.4444 | 6944.4444 | 6944.4444 | 6944.4444 | 6944.4444 | 6944.4444 | 6944.4444 | 6944.4444 | 6944.4444 | 6944.4444 | 6944.4444 | 250000 | 0
| Property Survey | 50000 | 13: 50000 | 50000 | 0
| Gaming Commission Fees | 40000 | 13: 40000 | 40000 | 0
| Gaming License legal | 40000 | 10: 3333.3333; 11: 3333.3333; 12: 3333.3333; 13: 3333.3333; 14: 3333.3333; 15: 3333.3333; 16: 3333.3333; 17: 3333.3333; 18: 3333.3333; 19: 3333.3333; 20: 3333.3333; 21: 3333.3333 | 40000 | 0
| Dulaney Law TIF Funding | 50000 | 5: 25000; 6: 25000 | 50000 | 0
| IMG Golf & Tennis | 250000 | 7: 83333.3333; 8: 83333.3333; 9: 83333.3333 | 250000 | 0
| Retail | 150000 | 7: 50000; 8: 50000; 9: 50000 | 150000 | 0
| Rogich Communication Group | 150000 | 7: 50000; 8: 50000; 9: 50000 | 150000 | 0
| Murphree Real Estate | 240000 | 7: 80000; 8: 80000; 9: 80000 | 240000 | 0
| Begley Casino Law | 50000 | 7: 16666.6667; 8: 16666.6667; 9: 16666.6667 | 50000 | 0
| Ervil Lee Casino Attorney | 50000 | 5: 25000; 6: 25000 | 50000 | 0
| Urban Planning Consulting Fees | 250000 | 4: 41666.6667; 5: 41666.6667; 6: 41666.6667; 7: 41666.6667; 8: 41666.6667; 9: 41666.6667 | 250000 | 0
| Architect Fees (Domes) | 1320000 | 13: 110000; 14: 110000; 15: 110000; 16: 110000; 17: 110000; 18: 110000; 19: 110000; 20: 110000; 21: 110000; 22: 110000; 23: 110000; 24: 110000 | 1320000 | 0
| Accounting | 145000 | 10: 12083.3333; 11: 12083.3333; 12: 12083.3333; 13: 12083.3333; 14: 12083.3333; 15: 12083.3333; 16: 12083.3333; 17: 12083.3333; 18: 12083.3333; 19: 12083.3333; 20: 12083.3333; 21: 12083.3333 | 145000 | 0
| Breazeale Saunders O'Neal CPA MS | 50000 | 5: 50000 | 50000 | 0
| Civil Engineering Fees | 2000000 | 10: 166666.6667; 11: 166666.6667; 12: 166666.6667; 13: 166666.6667; 14: 166666.6667; 15: 166666.6667; 16: 166666.6667; 17: 166666.6667; 18: 166666.6667; 19: 166666.6667; 20: 166666.6667; 21: 166666.6667 | 2000000 | 0
| Mississippi Water Mgm't. Study | 75000 | 13: 75000 | 75000 | 0
| Geotechnical Engineer | 75000 | 13: 75000 | 75000 | 0
| Archeologist Fees | 10000 | 13: 10000 | 10000 | 0
| Liability Insurance | 324000 | 10: 27000; 11: 27000; 12: 27000; 13: 27000; 14: 27000; 15: 27000; 16: 27000; 17: 27000; 18: 27000; 19: 27000; 20: 27000; 21: 27000 | 324000 | 0
| Environmental Impact Report | 220000 | 4: 220000 | 220000 | 0
| General & Administration | 350000 | 10: 29166.6667; 11: 29166.6667; 12: 29166.6667; 13: 29166.6667; 14: 29166.6667; 15: 29166.6667; 16: 29166.6667; 17: 29166.6667; 18: 29166.6667; 19: 29166.6667; 20: 29166.6667; 21: 29166.6667 | 350000 | 0
| Financing Fees | 600000 | 10: 50000; 11: 50000; 12: 50000; 13: 50000; 14: 50000; 15: 50000; 16: 50000; 17: 50000; 18: 50000; 19: 50000; 20: 50000; 21: 50000 | 600000 | 0
| Working Capital & Contingency | 1100000 | [9 empty] | 30555.5556 | 30555.5556 | 30555.5556 | 30555.5556 | 30555.5556 | 30555.5556 | 30555.5556 | 30555.5556 | 30555.5556 | 30555.5556 | 30555.5556 | 30555.5556 | 30555.5556 | 30555.5556 | 30555.5556 | 30555.5556 | 30555.5556 | 30555.5556 | 30555.5556 | 30555.5556 | 30555.5556 | 30555.5556 | 30555.5556 | 30555.5556 | 30555.5556 | 30555.5556 | 30555.5556 | 30555.5556 | 30555.5556 | 30555.5556 | 30555.5556 | 30555.5556 | 30555.5556 | 30555.5556 | 30555.5556 | 30555.5556 | 1100000 | 0
30 | COMPLETE RESORT TOTAL CAT.30 | 8024000 | [45 empty] | 8024000 | 0
0
10 | FF&E GUESTROOMS | [47 empty] | 0
100 | Guestrooms (2200) | 27500000 | 38: 4583333.3333; 39: 4583333.3333; 40: 4583333.3333; 41: 4583333.3333; 42: 4583333.3333; 43: 4583333.3333 | 27500000 | 0
200 | Suites (200) | 4000000 | 38: 666666.6667; 39: 666666.6667; 40: 666666.6667; 41: 666666.6667; 42: 666666.6667; 43: 666666.6667 | 4000000 | 0
250 | Villas & Condo's 100 ea | 4500000 | 38: 750000; 39: 750000; 40: 750000; 41: 750000; 42: 750000; 43: 750000 | 4500000 | 0
| 7% Sales Tax | 2520000 | 38: 420000; 39: 420000; 40: 420000; 41: 420000; 42: 420000; 43: 420000 | 2520000 | 0
300 | Freight | 1890000 | 38: 315000; 39: 315000; 40: 315000; 41: 315000; 42: 315000; 43: 315000 | 1890000 | 0
300 | Installation | 945000 | 38: 157500; 39: 157500; 40: 157500; 41: 157500; 42: 157500; 43: 157500 | 945000 | 0
300 | Warehousing | 1417500 | 38: 236250; 39: 236250; 40: 236250; 41: 236250; 42: 236250; 43: 236250 | 1417500 | 0
| sub-total "Category 10" | 42772500 | [45 empty] | 42772500 | 0
0
20 | FF&E PUBLIC AREAS | [47 empty] | 0
100 | Furnishings | 0 | [46 empty] | 0
100 | Public Areas | 20400000 | 38: 3400000; 39: 3400000; 40: 3400000; 41: 3400000; 42: 3400000; 43: 3400000 | 20400000 | 0
100 | Food & Beverage | 3750000 | 38: 625000; 39: 625000; 40: 625000; 41: 625000; 42: 625000; 43: 625000 | 3750000 | 0
100 | Meeting & Banquet | 19250000 | 38: 3208333.3333; 39: 3208333.3333; 40: 3208333.3333; 41: 3208333.3333; 42: 3208333.3333; 43: 3208333.3333 | 19250000 | 0
100 | Casino | 32000000 | 38: 5333333.3333; 39: 5333333.3333; 40: 5333333.3333; 41: 5333333.3333; 42: 5333333.3333; 43: 5333333.3333 | 32000000 | 0
100 | Spa | 1400000 | 38: 233333.3333; 39: 233333.3333; 40: 233333.3333; 41: 233333.3333; 42: 233333.3333; 43: 233333.3333 | 1400000 | 0
100 | Recreation | 1750000 | 38: 291666.6667; 39: 291666.6667; 40: 291666.6667; 41: 291666.6667; 42: 291666.6667; 43: 291666.6667 | 1750000 | 0
100 | Administration | 1500000 | 38: 250000; 39: 250000; 40: 250000; 41: 250000; 42: 250000; 43: 250000 | 1500000 | 0
300 | Freight & Installation | 6003750 | 38: 1000625; 39: 1000625; 40: 1000625; 41: 1000625; 42: 1000625; 43: 1000625 | 6003750 | 0
| 7% Sales Tax | 5603500 | 38: 933916.6667; 39: 933916.6667; 40: 933916.6667; 41: 933916.6667; 42: 933916.6667; 43: 933916.6667 | 5603500 | 0
400 | Millwork | 17000000 | 38: 2833333.3333; 39: 2833333.3333; 40: 2833333.3333; 41: 2833333.3333; 42: 2833333.3333; 43: 2833333.3333 | 17000000 | 0
420 | Wall Covering | 500000 | 38: 83333.3333; 39: 83333.3333; 40: 83333.3333; 41: 83333.3333; 42: 83333.3333; 43: 83333.3333 | 500000 | 0
440 | Stone | 1250000 | 38: 208333.3333; 39: 208333.3333; 40: 208333.3333; 41: 208333.3333; 42: 208333.3333; 43: 208333.3333 | 1250000 | 0
500 | Carpet | 2135895 | 38: 355982.5; 39: 355982.5; 40: 355982.5; 41: 355982.5; 42: 355982.5; 43: 355982.5 | 2135895 | 0
600 | Artwork | 500000 | 38: 83333.3333; 39: 83333.3333; 40: 83333.3333; 41: 83333.3333; 42: 83333.3333; 43: 83333.3333 | 500000 | 0
600 | Planters | 125000 | 38: 20833.3333; 39: 20833.3333; 40: 20833.3333; 41: 20833.3333; 42: 20833.3333; 43: 20833.3333 | 125000 | 0
610 | Interior Landscaping | 927000 | 38: 154500; 39: 154500; 40: 154500; 41: 154500; 42: 154500; 43: 154500 | 927000 | 0
700 | Signage | 600000 | 38: 100000; 39: 100000; 40: 100000; 41: 100000; 42: 100000; 43: 100000 | 600000 | 0
700 | Signs | 500000 | 38: 83333.3333; 39: 83333.3333; 40: 83333.3333; 41: 83333.3333; 42: 83333.3333; 43: 83333.3333 | 500000 | 0
750 | Lighting | 2400000 | 38: 400000; 39: 400000; 40: 400000; 41: 400000; 42: 400000; 43: 400000 | 2400000 | 0
800 | Retail | 50000 | 38: 8333.3333; 39: 8333.3333; 40: 8333.3333; 41: 8333.3333; 42: 8333.3333; 43: 8333.3333 | 50000 | 0
960 | Elevator Cabs | 300000 | 38: 50000; 39: 50000; 40: 50000; 41: 50000; 42: 50000; 43: 50000 | 300000 | 0
970 | GR & PA Contingency | 1000000 | 38: 166666.6667; 39: 166666.6667; 40: 166666.6667; 41: 166666.6667; 42: 166666.6667; 43: 166666.6667 | 1000000 | 0
| sub-total "Category 20" | 118945145 | [45 empty] | 118945145 | 0
0
30 | KITCHEN / LAUNDRY | [47 empty] | 0
100 | Kitchen Equipment | 5500000 | 41: 5500000 | 5500000 | 0
200 | Laundry Equipment | 2800000 | 41: 2800000 | 2800000 | 0
| sub-total "Category 30" | 8300000 | [45 empty] | 8300000 | 0
0
40 | EXPENDABLES | [47 empty] | 0
100 | Hotel Expendables | 6300000 | 41: 6300000 | 6300000 | 0
200 | Park Expendables | 2500000 | 41: 2500000 | 2500000 | 0
| sub-total "Category 40" | 8800000 | [45 empty] | 8800000 | 0
0
50 | BACK OF HOUSE | [47 empty] | 0
100 | Back of House | 840000 | 41: 840000 | 840000 | 0
| sub-total "Category 50" | 840000 | [45 empty] | 840000 | 0
0
100 | COMPUTER SYSTEMS | [47 empty] | 0
110 | PMS | 1800000 | 39: 1800000 | 1800000 | 0
120 | POS | 500000 | 39: 500000 | 500000 | 0
130 | Office Automation | 300000 | 39: 300000 | 300000 | 0
140 | Purchasing | 125000 | 39: 125000 | 125000 | 0
150 | Cable | 250000 | 39: 250000 | 250000 | 0
160 | Time & Attendance | 50000 | 39: 50000 | 50000 | 0
| sub-total "Category 100" | 3025000 | [45 empty] | 3025000 | 0
0
200 | TELEPHONES | [47 empty] | 0
210 | Telephones | 1200000 | 42: 1200000 | 1200000 | 0
220 | Wide Work Area Network | 2040000 | 42: 2040000 | 2040000 | 0
| sub-total "Category 200" | 3240000 | [45 empty] | 3240000 | 0
0
300 | AUDIO VISUAL | [47 empty] | 0
310 | A/V | 1500000 | 42: 1500000 | 1500000 | 0
320 | TV | 1800000 | 43: 1800000 | 1800000 | 0
330 | MATV | 150000 | 43: 150000 | 150000 | 0
| sub-total "Category 300" | 3450000 | [45 empty] | 3450000 | 0
0
400 | SECURITY | [47 empty] | 0
|  | 250000 | 43: 250000 | 250000 | 0
| sub-total "Category 400" | 250000 | [45 empty] | 250000 | 0
0
600 | EMPLOYEE COMMUNICATION | [47 empty] | 0
|  | 150000 | 43: 150000 | 150000 | 0
| sub-total "Category 600" | 150000
0
900 | MODEL ROOMS | [47 empty] | 0
|  | 500000 | 24: 500000 | 500000 | 0
| sub-total "Category 600" | 500000 | [45 empty] | 500000 | 0
0
80 | PURCHASING AGENT | [47 empty] | 0
100 | Purchasing Agent | 15221811.6 | 38: 2536968.6; 39: 2536968.6; 40: 2536968.6; 41: 2536968.6; 42: 2536968.6; 43: 2536968.6 | 15221811.6 | 0
| sub-total "Category 80" | 15221811.6 | [45 empty] | 15221811.6 | 0
0
90 | FF&E CONTIGENCY | [47 empty] | 0
100 | Contingency | 10274722.83 | 38: 1712453.805; 39: 1712453.805; 40: 1712453.805; 41: 1712453.805; 42: 1712453.805; 43: 1712453.805 | 10274722.83 | 0
| sub-total "Category 90" | 10274722.83 | [45 empty] | 10274722.83 | 0
0
30 | FF&E TOTAL CAT.30 | 215769179.43 | [45 empty] | 215769179.43 | 0
0
10 | DEVELOPMENT | [47 empty] | 0
100 | Dev. Fee | 48595715.537 | [9 empty] | 1349880.9871 | 1349880.9871 | 1349880.9871 | 1349880.9871 | 1349880.9871 | 1349880.9871 | 1349880.9871 | 1349880.9871 | 1349880.9871 | 1349880.9871 | 1349880.9871 | 1349880.9871 | 1349880.9871 | 1349880.9871 | 1349880.9871 | 1349880.9871 | 1349880.9871 | 1349880.9871 | 1349880.9871 | 1349880.9871 | 1349880.9871 | 1349880.9871 | 1349880.9871 | 1349880.9871 | 1349880.9871 | 1349880.9871 | 1349880.9871 | 1349880.9871 | 1349880.9871 | 1349880.9871 | 1349880.9871 | 1349880.9871 | 1349880.9871 | 1349880.9871 | 1349880.9871 | 1349880.9871 | 48595715.537 | 0
| sub-total "Category 10" | 48595715.537 | [45 empty] | 48595715.537 | 0
0
20 | TECHNICAL SERVICE | [47 empty] | 0
100 | TAS Fee | 750000 | 16: 125000; 17: 125000; 18: 125000; 19: 125000; 20: 125000; 21: 125000 | 750000 | 0
| sub-total "Category 20" | 750000 | [45 empty] | 750000 | 0
0
30 | FINANCE | [47 empty] | 0
100 | Debt Placement Fees | 0 | 10: 0 | 0 | 0
100 | Brokerage Fees | 48000000 | [9 empty] | 1333333.3333 | 1333333.3333 | 1333333.3333 | 1333333.3333 | 1333333.3333 | 1333333.3333 | 1333333.3333 | 1333333.3333 | 1333333.3333 | 1333333.3333 | 1333333.3333 | 1333333.3333 | 1333333.3333 | 1333333.3333 | 1333333.3333 | 1333333.3333 | 1333333.3333 | 1333333.3333 | 1333333.3333 | 1333333.3333 | 1333333.3333 | 1333333.3333 | 1333333.3333 | 1333333.3333 | 1333333.3333 | 1333333.3333 | 1333333.3333 | 1333333.3333 | 1333333.3333 | 1333333.3333 | 1333333.3333 | 1333333.3333 | 1333333.3333 | 1333333.3333 | 1333333.3333 | 1333333.3333 | 48000000 | 0
100 | Finance Fees | 0 | 10: 0 | 0 | 0
100 | Interest | 11625000 | 4: 645833.3333; 5: 645833.3333; 6: 645833.3333; 7: 645833.3333; 8: 645833.3333; 9: 645833.3333; 10: 645833.3333; 11: 645833.3333; 12: 645833.3333; 13: 645833.3333; 14: 645833.3333; 15: 645833.3333; 16: 645833.3333; 17: 645833.3333; 18: 645833.3333; 19: 645833.3333; 20: 645833.3333; 21: 645833.3333 | 11625000 | 0
200 | Equity | [46 empty] | 0 | 0
| Equity Return | [46 empty] | 0 | 0
| Reinvestment | [46 empty] | 0 | 0
300 | Appraisal | 500000 | 16: 500000 | 500000 | 0
400 | Lenders Consultant | 150000 | 17: 150000 | 150000 | 0
| sub-total "Category 30" | 60275000 | [45 empty] | 60275000 | 0
0
40 | LEGAL & ACCOUNTING | [47 empty] | 0
100 | Legal Department | [47 empty] | 0
110 | Legal Acquisition | [47 empty] | 0
500 | Tax Consultant | [47 empty] | 0
| sub-total "Category 40" | 1250000 | 13: 104166.6667; 14: 104166.6667; 15: 104166.6667; 16: 104166.6667; 17: 104166.6667; 18: 104166.6667; 19: 104166.6667; 20: 104166.6667; 21: 104166.6667; 22: 104166.6667; 23: 104166.6667; 24: 104166.6667 | 1250000 | 0
0
50 | PROJECT ADMINISTRATION | [47 empty] | 0
100 | Salaries | 23074740.36 | [9 empty] | 320482.505 | 320482.505 | 320482.505 | 640965.01 | 640965.01 | 640965.01 | 640965.01 | 961447.515 | 961447.515 | 961447.515 | 640965.01 | 640965.01 | 640965.01 | 640965.01 | 640965.01 | 640965.01 | 640965.01 | 640965.01 | 640965.01 | 640965.01 | 640965.01 | 640965.01 | 640965.01 | 640965.01 | 640965.01 | 640965.01 | 640965.01 | 640965.01 | 640965.01 | 640965.01 | 640965.01 | 640965.01 | 640965.01 | 640965.01 | 640965.01 | 640965.01 | 23074740.36 | 0
| Phase 1 C M Fees | 700000 | 4: 116666.6667; 5: 116666.6667; 6: 116666.6667; 7: 116666.6667; 8: 116666.6667; 9: 116666.6667 | 700000 | 0
150 | OH & Administration | 3500000 | 1: 875000; 2: 875000; 3: 875000; 4: 875000 | 3500000
200 | Field Ofc Expenses | 420000 | [9 empty] | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 420000 | 0
300 | Travel & Ent. | 420000 | [9 empty] | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 11666.6667 | 420000 | 0
500 | Miscellaneous | 350000 | [9 empty] | 9722.2222 | 9722.2222 | 9722.2222 | 9722.2222 | 9722.2222 | 9722.2222 | 9722.2222 | 9722.2222 | 9722.2222 | 9722.2222 | 9722.2222 | 9722.2222 | 9722.2222 | 9722.2222 | 9722.2222 | 9722.2222 | 9722.2222 | 9722.2222 | 9722.2222 | 9722.2222 | 9722.2222 | 9722.2222 | 9722.2222 | 9722.2222 | 9722.2222 | 9722.2222 | 9722.2222 | 9722.2222 | 9722.2222 | 9722.2222 | 9722.2222 | 9722.2222 | 9722.2222 | 9722.2222 | 9722.2222 | 9722.2222 | 350000 | 0
| sub-total "Category 50" | 28464740.36 | [45 empty] | 28464740.36 | 0
0
60 | DEVELOPMENT EXPENSES | [47 empty] | 0
100 | Predevelopment Costs | 6000000 | 22: 500000; 23: 500000; 24: 500000; 25: 500000; 26: 500000; 27: 500000; 28: 500000; 29: 500000; 30: 500000; 31: 500000; 32: 500000; 33: 500000 | 6000000 | 0
| Predevelopment Costs to be reimbursed | 1200000 | 4: 200000; 5: 200000; 6: 200000; 7: 200000; 8: 200000; 9: 200000 | 1200000 | 0
200 | Title Insurance | 1404088.0051 | [9 empty] | 39002.4446 | 39002.4446 | 39002.4446 | 39002.4446 | 39002.4446 | 39002.4446 | 39002.4446 | 39002.4446 | 39002.4446 | 39002.4446 | 39002.4446 | 39002.4446 | 39002.4446 | 39002.4446 | 39002.4446 | 39002.4446 | 39002.4446 | 39002.4446 | 39002.4446 | 39002.4446 | 39002.4446 | 39002.4446 | 39002.4446 | 39002.4446 | 39002.4446 | 39002.4446 | 39002.4446 | 39002.4446 | 39002.4446 | 39002.4446 | 39002.4446 | 39002.4446 | 39002.4446 | 39002.4446 | 39002.4446 | 39002.4446 | 1404088.0051 | 0
300 | Taxes During Const. | 5167304.6728 | 22: 215304.3614; 23: 215304.3614; 24: 215304.3614; 25: 215304.3614; 26: 215304.3614; 27: 215304.3614; 28: 215304.3614; 29: 215304.3614; 30: 215304.3614; 31: 215304.3614; 32: 215304.3614; 33: 215304.3614; 34: 215304.3614; 35: 215304.3614; 36: 215304.3614; 37: 215304.3614; 38: 215304.3614; 39: 215304.3614; 40: 215304.3614; 41: 215304.3614; 42: 215304.3614; 43: 215304.3614; 44: 215304.3614; 45: 215304.3614 | 5167304.6728 | 0
400 | Builder Risk Ins. | 15501914.0183 | 22: 15501914.0183 | 15501914.0183 | 0
450 | Liability Ins. | 15501914.0183 | 22: 15501914.0183 | 15501914.0183 | 0
500 | Inspection | 2500000 | 22: 104166.6667; 23: 104166.6667; 24: 104166.6667; 25: 104166.6667; 26: 104166.6667; 27: 104166.6667; 28: 104166.6667; 29: 104166.6667; 30: 104166.6667; 31: 104166.6667; 32: 104166.6667; 33: 104166.6667; 34: 104166.6667; 35: 104166.6667; 36: 104166.6667; 37: 104166.6667; 38: 104166.6667; 39: 104166.6667; 40: 104166.6667; 41: 104166.6667; 42: 104166.6667; 43: 104166.6667; 44: 104166.6667; 45: 104166.6667 | 2500000 | 0
600 | Misc. Exp. | 150000 | [9 empty] | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 4166.6667 | 150000 | 0
700 | Public Relations | 500000 | [9 empty] | 13888.8889 | 13888.8889 | 13888.8889 | 13888.8889 | 13888.8889 | 13888.8889 | 13888.8889 | 13888.8889 | 13888.8889 | 13888.8889 | 13888.8889 | 13888.8889 | 13888.8889 | 13888.8889 | 13888.8889 | 13888.8889 | 13888.8889 | 13888.8889 | 13888.8889 | 13888.8889 | 13888.8889 | 13888.8889 | 13888.8889 | 13888.8889 | 13888.8889 | 13888.8889 | 13888.8889 | 13888.8889 | 13888.8889 | 13888.8889 | 13888.8889 | 13888.8889 | 13888.8889 | 13888.8889 | 13888.8889 | 13888.8889 | 500000 | 0
700 | Transportation | 360000 | [9 empty] | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 360000 | 0
800 | Retail | 150000 | 17: 25000; 18: 25000; 19: 25000; 20: 25000; 21: 25000; 22: 25000 | 150000 | 0
900 | Retail Broker | 350000 | 17: 58333.3333; 18: 58333.3333; 19: 58333.3333; 20: 58333.3333; 21: 58333.3333; 22: 58333.3333 | 350000 | 0
| sub-total "Category 60" | 48785220.7146 | [45 empty] | 48785220.7146 | 0
0
70 | FUNDING INTEREST | [47 empty] | 0
100 | Interest Expenses thru 42 months | [47 empty] | 0
| ( Months 2 thru Month 42 | 184814086.8885 |  |  |  |  | 259938.7671 | 337499.7103 | 410966.1861 | 479141.4316 | 547380.4905 | 614266.8514 | 648225.2093 | 684130.842 | 736913.2723 | 801550.7991 | 914360.9367 | 1028411.5709 | 1145683.5316 | 1262980.3516 | 1407753.1959 | 1532715.1735 | 1656535.632 | 1782605.3022 | 2269548.1124 | 2532565.8899 | 2798555.7747 | 3060402.2999 | 3339192.3849 | 3619607.6419 | 4110698.661 | 4604653.2404 | 5087410.0465 | 5572981.7634 | 6044517.9063 | 6518803.4737 | 6999291.2941 | 7482580.7263 | 7968688.0982 | 8457629.8336 | 9131436.2378 | 9826817.7226 | 10298663.1699 | 10877909.7345 | 11383533.9117 | 11878164.5604 | 24982255.0136 | 185096966.7518
| Interest Expense | 0 | [45 empty] | 0
| sub-total "Category 70" | 184814086.8885 | [46 empty] | 184814086.8885
0
80 | DEVELOPMENT CONTIGENCY | [47 empty] | 0
100 | Contingency | 56535309.9633 | [13 empty] | 1766728.4364 | 1766728.4364 | 1766728.4364 | 1766728.4364 | 1766728.4364 | 1766728.4364 | 1766728.4364 | 1766728.4364 | 1766728.4364 | 1766728.4364 | 1766728.4364 | 1766728.4364 | 1766728.4364 | 1766728.4364 | 1766728.4364 | 1766728.4364 | 1766728.4364 | 1766728.4364 | 1766728.4364 | 1766728.4364 | 1766728.4364 | 1766728.4364 | 1766728.4364 | 1766728.4364 | 1766728.4364 | 1766728.4364 | 1766728.4364 | 1766728.4364 | 1766728.4364 | 1766728.4364 | 1766728.4364 | 1766728.4364 | 56535309.9633 | 0
| sub-total "Category 80" | 56535309.9633 | [45 empty] | 56535309.9633 | 0
0
40 | DVL'T/FIN. TOTAL CAT.(10+20+30+40+50+60+70+80) | 429470073.4634 | [45 empty] | 429470073.3266 | 0.13675
0
10 | PRE-OPENING EXPENSES | [47 empty] | 0
100 | Pre-Opening Expenses | 25000000 | 34: 2083333.3333; 35: 2083333.3333; 36: 2083333.3333; 37: 2083333.3333; 38: 2083333.3333; 39: 2083333.3333; 40: 2083333.3333; 41: 2083333.3333; 42: 2083333.3333; 43: 2083333.3333; 44: 2083333.3333; 45: 2083333.3333 | 25000000 | 0
100 | Working Capital / operations | 23490000 | [17 empty] | 838928.5714 | 838928.5714 | 838928.5714 | 838928.5714 | 838928.5714 | 838928.5714 | 838928.5714 | 838928.5714 | 838928.5714 | 838928.5714 | 838928.5714 | 838928.5714 | 838928.5714 | 838928.5714 | 838928.5714 | 838928.5714 | 838928.5714 | 838928.5714 | 838928.5714 | 838928.5714 | 838928.5714 | 838928.5714 | 838928.5714 | 838928.5714 | 838928.5714 | 838928.5714 | 838928.5714 | 838928.5714 | 23490000 | 0
200 | IMG Event Budget | 57850000 | [13 empty] | 1807812.5 | 1807812.5 | 1807812.5 | 1807812.5 | 1807812.5 | 1807812.5 | 1807812.5 | 1807812.5 | 1807812.5 | 1807812.5 | 1807812.5 | 1807812.5 | 1807812.5 | 1807812.5 | 1807812.5 | 1807812.5 | 1807812.5 | 1807812.5 | 1807812.5 | 1807812.5 | 1807812.5 | 1807812.5 | 1807812.5 | 1807812.5 | 1807812.5 | 1807812.5 | 1807812.5 | 1807812.5 | 1807812.5 | 1807812.5 | 1807812.5 | 1807812.5 | 57850000 | 0
100 | Operating Shortfalls | 10000000 | 45: 10000000 | 10000000 | 0
| sub-total "Category 10" | 116340000 | [45 empty] | 116340000 | 0
50 | OPERATIONS TOTAL - CAT.10 | 116340000 | [45 empty] | 116340000 | 0
0
0
TOTAL PROJECT COSTS |  | 2173691258.0312 | [45 empty] | 2173691257.8944 | 0.13675
|  | 2173691258.0312 | 12555000 | 875000 | 875000 | 44560931.5 | 13154756.2671 | 12707317.2103 | 11794117.0195 | 11612292.2649 | 11380531.3238 | 5735865.7785 | 6069824.1363 | 8963134.0941 | 10995583.9637 | 19253896.4354 | 19466706.573 | 20019090.5405 | 20023511.6729 | 24733849.7807 | 21337866.699 | 21142346.1717 | 21528096.7762 | 83392238.0152 | 45005266.9506 | 45514951.3948 | 44804844.4668 | 47709640.9919 | 47988431.077 | 84104468.1007 | 84595559.1198 | 82676138.6991 | 83158895.5053 | 80753000.5555 | 81224536.6983 | 82287988.9325 | 82768476.7529 | 83251766.1851 | 83737873.557 | 115429178.5306 | 119127984.9349 | 80807744.6531 | 99219590.1004 | 86598836.6649 | 84714460.8421 | 51656728.2525 | 74760818.7057 | 2173691257.8944 | 0.13675
|  |  | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month | TOTAL
| DESCRIPTION |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45
|  | TOTAL | 12555000 | 875000 | 875000 | 44560931.5 | 13154756.2671 | 12707317.2103 | 11794117.0195 | 11612292.2649 | 11380531.3238 | 5735865.7785 | 6069824.1363 | 8963134.0941 | 10995583.9637 | 19253896.4354 | 19466706.573 | 20019090.5405 | 20023511.6729 | 24733849.7807 | 21337866.699 | 21142346.1717 | 21528096.7762 | 83392238.0152 | 45005266.9506 | 45514951.3948 | 44804844.4668 | 47709640.9919 | 47988431.077 | 84104468.1007 | 84595559.1198 | 82676138.6991 | 83158895.5053 | 80753000.5555 | 81224536.6983 | 82287988.9325 | 82768476.7529 | 83251766.1851 | 83737873.557 | 115429178.5306 | 119127984.9349 | 80807744.6531 | 99219590.1004 | 86598836.6649 | 84714460.8421 | 51656728.2525 | 74760818.7057 | 2173691257.8944
|  | TOTAL | 12555000 | 875000 | 875000 | 44560931.5 | 13154756.2671 | 12707317.2103 | 11794117.0195 | 11612292.2649 | 11380531.3238 | 5735865.7785 | 6069824.1363 | 8963134.0941 | 10995583.9637 | 19253896.4354 | 19466706.573 | 20019090.5405 | 20023511.6729 | 24733849.7807 | 21337866.699 | 21142346.1717 | 21528096.7762 | 83392238.0152 | 45005266.9506 | 45514951.3948 | 44804844.4668 | 47709640.9919 | 47988431.077 | 84104468.1007 | 84595559.1198 | 82676138.6991 | 83158895.5053 | 80753000.5555 | 81224536.6983 | 82287988.9325 | 82768476.7529 | 83251766.1851 | 83737873.557 | 115429178.5306 | 119127984.9349 | 80807744.6531 | 99219590.1004 | 86598836.6649 | 84714460.8421 | 51656728.2525 | 74760818.7057 | 2173691257.8944
|  | Cumulative | 12555000 | 13430000 | 14305000 | 58865931.5 | 72020687.7671 | 84728004.9774 | 96522121.9969 | 108134414.2618 | 119514945.5856 | 125250811.3641 | 131320635.5004 | 140283769.5945 | 151279353.5581 | 170533249.9935 | 189999956.5666 | 210019047.1071 | 230042558.78 | 254776408.5607 | 276114275.2598 | 297256621.4314 | 318784718.2077 | 402176956.2229 | 447182223.1735 | 492697174.5682 | 537502019.0351 | 585211660.027 | 633200091.104 | 717304559.2047 | 801900118.3245 | 884576257.0237 | 967735152.529 | 1048488153.0845 | 1129712689.7828 | 1212000678.7153 | 1294769155.4682 | 1378020921.6532 | 1461758795.2102 | 1577187973.7409 | 1696315958.6758 | 1777123703.3288 | 1876343293.4292 | 1962942130.0941 | 2047656590.9362 | 2099313319.1888 | 2174074137.8944
|  |  | LAND & MOBILIZATION |  |  | LAND, SITE CIVIL, SITE INFRASTRUCTURE, DESIGN & SOFT COSTS